## ISO27001 Risk Register
Risk ID | Asset/Process | Risk Description | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Owner | Existing Controls | Treatment Option | Action Plan | Target Date | Status | ISO 27001 Control Reference
R-001 | Customer Data | Unauthorized access to customer data | External attacker | Weak passwords | 4 | 5 | 20 | IT Manager | MFA enabled | Mitigate | Implement password policy | 2026-06-30 | Open | A.5, A.8
R-002 | Email System | Phishing attack | Phishing | Lack of awareness | 4 | 4 | 16 | Security Officer | Email filtering | Mitigate | User awareness training | 2026-03-31 | Open | A.6
R-003 | Server Infrastructure | Service outage | Hardware failure | Single point of failure | 3 | 5 | 15 | IT Manager | Backups | Mitigate | Add redundancy | 2026-09-30 | Open | A.8
R-004 | Endpoints | Malware infection | Malware | Missing patches | 3 | 4 | 12 | Desktop Admin | EDR | Mitigate | Improve patching | 2026-04-30 | Open | A.8
R-005 | HR Records | Data leakage | Insider threat | Excessive permissions | 2 | 5 | 10 | HR Manager | Access reviews | Mitigate | Least privilege review | 2026-05-31 | Open | A.5